## Past Winners & Patterns
Event | Year | Project / Winner | Builders | What it did | Tech Stack Notes | Why it won (pattern) | Source
Runway Characters Hackathon | 2026 | Various (Yining Shi-led) | In-person, NYC | Real-time interactive video agents on Characters (GWM-1) — first developer event for the new model. | Characters API + custom audio drivers | Novelty alignment: judges led by Yining Shi rewarded teams that pushed Characters past demo-stage. | https://x.com/runwayml/status/2040114843215188127
Runway Gen:48 | 2025 | Multiple finalists; Gen:48 is a 48-hour AI-film comp | Indie filmmaker teams worldwide | 48-hour AI-generated short films on a theme prompt. | Mostly Gen-3 / Gen-4 + audio editors | Storytelling craft + cinematic visual quality — narrative coherence beats novelty. | https://runwayml.com/gen48/terms
AIFF (AI Film Festival) | 2024-2025 | Curated selections, jury-judged | Filmmaker teams; jury includes industry pros | Annual AI-film festival with feature screenings, jury-selected winners. | Multi-tool AI workflows; not API-focused | Aesthetic + emotional resonance + technical ambition. Different rubric from this hackathon. | https://aiff.runwayml.com/
Runway API Hackathon | May 2026 | TBD — this is the event we're entering | Open registration, virtual | Three-day virtual hackathon for agents/apps/tools/workflows on Runway API. | Runway API + Modal + LLM + audio | (Predicted) Practical problem-solving + sophisticated API integration + polish. | https://runwayml.com/api-hackathon
Microsoft AI Agents Hackathon | 2025 | RiskWise ($20K) | Solo/small team | Supply-chain risk analysis agent with multi-turn reasoning over structured data. | Azure AI + structured retrieval | Vertical specificity (supply chain) + grounded data + practical ROI beat horizontal demos. | https://microsoft.github.io/AI_Agents_Hackathon/winners/
Microsoft AI Agents Hackathon | 2025 | Apollo Deep Research Meta-Agent | Small team | Multi-turn reasoning agent over research datasets. | LLM + retrieval | Multi-turn reasoning over single-call usage; production-feeling output. | https://microsoft.github.io/AI_Agents_Hackathon/winners/
Microsoft AI Agents Hackathon | 2025 | Tariffed | Small team | Tariff-management agent for customs workflows. | Agent + structured APIs | Vertical specificity in a B2B niche. | https://microsoft.github.io/AI_Agents_Hackathon/winners/
HuggingFace Agents-MCP Hackathon | 2025 | Immersia (formerly LLMGameHub) | Small team | Generative narrative agent: world + genre + character → AI-generated story with image + audio. | MCP + generative image + adaptive audio | Combined narrative agents + generative media + adaptive audio = compelling demo. | https://huggingface.co/blog/kikikita/immersia-ai-games
OpenAI Open Model Hackathon | Feb 2026 | Rippletide | Small team | Multi-agent system for autonomous, continuous scientific discovery. | Multi-agent loop + LLMs | Systems that run autonomously between cycles beat one-shot tools. | https://openai.com/blog/
Vercel Gen CX Hackathon | 2025 | Gen CX winners (brand-content focus) | Small teams | Brand-content generation agents with rapid Vercel deployment. | Vercel AI Gateway + v0 + partner LLMs | Creator/marketing focus + integrated stack + one-click deploy. | https://vercel.com/blog/
Modal Hackathons (cumulative) | 2024-2026 | Various winners | Small teams | Various — typically GPU-heavy serverless inference apps. | Modal serverless + GPUs + custom models | Demonstrated infrastructure maturity + working production deploy. | https://modal.com/blog

## API Capabilities
Surface | Released | Cost (credits) | Latency | Best For | Hackathon Novelty Weight | DirectorOS Use
Gen-4.5 (text/image-to-video) | Feb 10, 2026 | 12/sec (60–120 per clip) | 30–60 sec | B-roll, scene generation, native audio | MEDIUM (proven, stable) | Primary B-roll engine
Characters / GWM-1 (real-time avatar) | Mar 9, 2026 | Not separately disclosed | Real-time (<500ms target) | Interactive avatars, narrator, conversational agents | HIGHEST (newest) | Narrator avatar; live-feeling preview
Act-Two (performance capture) | ~Feb 2026 | Not separately disclosed | Seconds | Motion-cap from webcam → animated character | HIGH (unique via API) | Optional: creator-recorded performance shots
Aleph (in-context cinematic editing) | 2025 | ~12/sec est. | 60–120 sec | Edit, relight, style match, scene regen | MEDIUM | Color/style consistency pass
gen4_image | 2025 | 5/image | Seconds | Reference frames, concept art, style anchors | MEDIUM | Character / style reference frames
ElevenLabs TTS via Runway | Sep 25, 2025 | ~0.5/100 chars est. | Seconds | 29-language VO, dubbing | MEDIUM | Multilingual VO
ElevenLabs Dubbing via Runway | Sep 25, 2025 | Bundled | Seconds | Translate video while preserving voice | MEDIUM | Per-platform/language outputs
Custom Voice Training | 2025 | 300/voice (one-time) | Minutes | Brand voices, creator clones | LOW (table-stakes) | Optional founder voice
Webhooks (Svix) | — | Free | Real-time event push | Async pipelines without polling | LOW | Pipeline plumbing
Runway Skills framework | Mar 2026 | Free (open source) | — | Agent-callable skills | MEDIUM (judge bait) | Three custom skills shipped to GitHub
Modal serverless (A100 40GB) | — | $2.10/hr base | Seconds | ffmpeg, post-processing, orchestration | LOW | Pipeline runtime

## Build Scorecard
Candidate | Creativity (1-5) | Technical Depth (1-5) | Impact (1-5) | Polish-feasibility in 72h (1-5) | Total (auto) | NumberOneSon Fit (1-5) | Combined (auto) | Notes
DirectorOS (recommended) | 5 | 5 | 5 | 4 | 19 | 5 | 24 | Anchor product line; solopreneur creator stack play; productizable in 30 days post-event.
InteractiveFlow (live narrative voting) | 5 | 5 | 4 | 3 | 17 | 3 | 20 | Twitch-creator niche; real-time risk; novel interaction model wows judges.
PerformanceAI (Act-Two performance) | 4 | 5 | 4 | 3 | 16 | 3 | 19 | Heavy Act-Two use; novel; demo-worthy; smaller market.
NewsFlow (live data → video) | 4 | 4 | 4 | 3 | 15 | 3 | 18 | Strong vertical (news/finance) but B2B sales cycle is longer than NOS solo thesis prefers.
EditBot (agentic post-production) | 3 | 5 | 4 | 2 | 14 | 2 | 16 | Pro market; high technical complexity; harder to demo end-to-end in 72h.

## Credit Budget
Bucket | Allocation (credits) | % of total | Retail $ | Notes
Pre-hack dev (May 6-7) | 20000 | 10% | 200 | Use 20K of the 50K participant credits before Friday kickoff for Runway API spikes.
Hackathon build (Fri-Sun) | 80000 | 40% | 800 | Gen-4.5 main pipeline + Characters tests + Act-Two trials + Aleph passes.
Demo recording (Sun) | 40000 | 20% | 400 | Generate canonical demo at full quality + 4K upscale + multilingual VO.
Edge-case battery (Sun) | 30000 | 15% | 300 | Blank input, 10K-char input, special chars, non-English, very long, broken refs.
Reserve / surprise | 30000 | 15% | 300 | Day-of-Friday endpoint announcements, judging-day backup runs.
TOTAL | 200000 | 100% | 2000 | Cap; track real-time in Supabase counter.

## 7-Day Plan
Date | Day | Theme | Outputs by EOD | Owner | Status
2026-05-05 | Tue T-3 | Decide & confirm (research-only) | Roger picks build. Runway dev account confirmed (roger@grubb.net validated). Discord joined. GitHub org created (empty). NO code written. | Roger + Claude | in progress
2026-05-06 | Wed T-2 | Research + interviews (no code) | Read full Runway docs + Skills repo + Modal docs. 5 user interviews. Architecture diagram. README outline. Brand decision. | Claude | pending
2026-05-07 | Thu T-1 | Env setup + spec freeze | Registration deadline 5pm ET — confirm enrolled. Install SDKs locally. Modal account ready. Slack workspace prepared. PRD frozen. NO API calls. NO submission code. | Claude | pending
2026-05-08 | Fri Day 1 | Hackathon Day 1 | Watch 9am ET kickoff + 10am ET walkthrough. Add Characters + Act-Two integrations. Multi-shot orchestration online. First full pipeline test by 5pm ET. | Claude + Roger | pending
2026-05-09 | Sat Day 2 | Fill-in + judge loop | LLM-as-judge regen loop. Aleph color pass. Multilingual VO. Per-platform crops. | Claude + Roger | pending
2026-05-10 | Sun Day 3 | Polish + demo | 25-case edge battery. Record canonical 3-min demo video. README v2. Public deploy. | Claude + Roger | pending
2026-05-11 | Mon Submit | Submit by 9am ET | Final smoke test. Submit. Cross-post on X tagging @runwayml @c_valenzuelab @yining_shi. DM Yining with clip. | Roger | pending

## Risk Register
Risk | Severity | Probability | Score (auto) | Mitigation
Originality clause (Section 7.3.1) — pre-built code disqualifies submission. | 5 | 4 | 20 | HARD RULE on Wed/Thu prep: NO submission code, NO submission API calls. Allowable prep: docs, interviews, architecture, env setup, README outline, brand. Any code or API output that ends up in the submission must be created May 8-11.
Roger's email is not the Runway API account email; registration silently rejects. | 5 | 4 | 20 | VERIFY TODAY: log in at dev.runwayml.com with roger@grubb.net. If not, sign up immediately and re-submit registration.
Registration deadline (Thu May 7, 5pm ET) closes; Runway dev account not provisioned in time. | 5 | 3 | 15 | Sign up at dev.runwayml.com TODAY. Confirm registration confirmation email arrives within 24 hours.
Characters / Act-Two API instability — both shipped <90 days ago. | 4 | 3 | 12 | Gen-4.5 fallback path for any shot type. Characters becomes a wow-feature, not critical-path.
Content moderation cascades to account suspension. | 5 | 2 | 10 | Pre-filter inputs client-side. Avoid public figures and recognizable artists. Test friendly first.
Credits depleted before submission. | 4 | 3 | 12 | Real-time Supabase counter. Hard cap at 80% (160K) until Sunday afternoon. $50 reserve buy if needed.
API Project must be publicly viewable/usable at submission. | 3 | 3 | 9 | Deploy to public URL with anonymous access OR include guest credentials in README. Slack OAuth must work for fresh installs.
Cannot edit submission after submit (Rule 6). | 4 | 2 | 8 | Submit at LATEST safe moment Monday morning after final 90-min smoke test. Kill-switch if public URL broken.
LinkedIn URL on registration form points to wrong profile. | 2 | 1 | 2 | Already filled with linkedin.com/in/rogergrubb-sf/. Confirm before clicking Register.
Slack OAuth approval delays prod readiness. | 3 | 3 | 9 | Use Slack workspace we control for the demo. Showcase OAuth in demo video frame, not live.
Multiple teams build the same pattern. | 3 | 4 | 12 | Differentiate via Characters narrator + Act-Two performance + LLM-as-judge regen loop.